## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact th> | Risk Score | Owner | Current Status | Mitigation Plan | Last Reviewed Date
R-001 | Cybersecurity breach due to outdated software | IT Security | High | Critical | 9 | IT Manager, Jane Doe | Active | Patch all systems; implement automated monitoring. | 2024-03-15
R-002 | Supply chain disruption from key vendor failure | Operational Risk | Medium | High | 7 | Procurement Lead, John Smith | Monitoring | Diversify vendor base; establish backup suppliers. | 2024-04-01
R-003 | Data privacy violation during employee onboarding | Compliance | Low | Medium | 4 | HR Director, Sarah Lee | Planned Review | Update onboarding forms with data handling consent. | 2024-05-10