## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Rating | Current Control Measures | Owner | Due Date | Status
R-001 | System outage due to unpatched software vulnerabilities | Technical | High | Critical | High | Automated patching, regular audits | IT Security Team | 2024-06-30 | Active
R-002 | Data breach from third-party vendor access | Operational | Medium | High | Medium | Vendor access review, MFA implementation | Compliance Officer | 2024-07-15 | Pending Review
R-003 | Business interruption from natural disasters | Environmental | Low | Critical | High | Disaster recovery plan, backup sites | Operations Manager | 2024-08-05 | In Progress
R-004 | Insufficient employee training on security protocols | Human Resources | Medium | Moderate | Medium | Quarterly training programs, awareness campaigns | HR Director | 2024-09-30 | Planned