## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Risk Rating | Ownership Team | Mitigation Strategy | Status | Last Reviewed Date
RISK-001 | Failure of network infrastructure during peak usage | IT Operations | Medium | High | Potential Impact (4/10) | Network Engineering Team | Redundant servers and load balancing setup | Ongoing | 2023-10-15
RISK-002 | Data breach due to outdated software vulnerabilities | Security | High | <Critical | Critical (9/10) | Security Operations Team | Patch management and penetration testing quarterly | Active Monitoring | 2023-11-03
RISK-003 | Supply chain delay affecting product delivery timelines | Logistics | Medium | Moderate | Moderate (5/10) | Operations & Supply Chain Team | Diversify suppliers and maintain buffer inventory | Planned Action | 2023-12-01