## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Status | Owner | Mitigation Strategy | Detection Method | Due Date
RISK-001 | System outage due to server failure | Operational Risk | High | High | Active | IT Operations Team | Implement redundant servers and automated failover. | Monitoring tools & alerting system | 2024-06-30
RISK-002 | Data breach from unsecured access points | Security Risk | Medium | Critical | Pending Review | Cybersecurity Officer | Enforce multi-factor authentication and access reviews. | Firewall logs and audit trails | 2024-07-15
RISK-003 | Supply chain delay affecting delivery timelines | Operational Risk | Medium | High | Active | Procurement Manager | Diversify suppliers and maintain safety stock. | Vendor performance tracking | 2024-08-10