## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Rating | Mitigation Strategy | Responsible Team Member | Due Date
System Downtime | Unplanned outages of critical infrastructure due to hardware failure. | High | High | Severity: High | Implement redundant servers and regular health checks. | Jane Doe (IT Operations) | 2024-05-15
Data Breach | Unauthorized access to sensitive customer data. | Medium | High | Severity: High | Enforce encryption, multi-factor authentication, and conduct quarterly audits. | Mark Smith (Security Team) | 2024-06-30
Compliance Failure | Misalignment with regulatory requirements. | Medium | Medium | Severity: Medium | Schedule biannual compliance reviews and training sessions. | Lisa Chen (Legal & Compliance) | 2024-07-10
Third-Party Vendor Risk | Unreliable or unethical vendor performance. | Low | High | Severity: High | Establish vendor assessment and contract compliance protocols. | Roger Brown (Procurement) | 2024-08-05