## Worksheet
Date | Asset/Equipment | Risk Identified | Risk Level (Low/Medium/High/Critical) | Impact Assessment | Likelihood of Occurrence | Mitigation Strategy | Responsible Party | Status (Open/Resolved) | Review Date
2024-03-15 | Main Power Generator | Overheating during high-load operation | High | Severe equipment damage, production downtime | Medium | Install cooling system upgrade and implement temperature monitoring | Maintenance Team Lead | Open | 2024-06-15
2024-03-20 | Chemical Storage Tank A | Leak potential due to aging seal | Critical | Environmental hazard, regulatory violation risk | High | Replace seals and conduct structural integrity inspection within 30 days | Safety Officer | Open | 2024-05-20
2024-03-25 | Production Line 3 | Mechanical failure due to vibration overload | Medium | Minor production delay, equipment repair cost | Low | Install vibration dampers and schedule preventive maintenance every 6 months | Operations Manager | Resolved | 2024-03-30
2024-04-01 | Filtration System B | Clogging due to particulate buildup | Low | Reduced efficiency, increased operational cost | Medium | Implement automated cleaning cycle and filter monitoring protocol | Maintenance Technician | Open | 2024-07-01