## Worksheet
Date | Asset Name | Location | Risk Level | Risk Description | Mitigation Action | Responsible Person | Due Date | Status
2024-04-05 | Production Line A | Factory Floor, Zone 3 | High | Potential overheating leading to equipment failure | Install temperature monitoring sensors and upgrade cooling system | Jane Smith | 2024-05-10 | In Progress
2024-04-12 | Server Room Cooling Unit | Building B, Subfloor 2 | Moderate | Unscheduled power outages affecting data integrity | Add backup UPS and implement redundant power supply | Mark Johnson | 2024-05-01 | Pending Approval
2024-04-20 | Warehouse Conveyor Belt | Storage Wing C | High | Potential mechanical failure causing material loss | Conduct monthly inspections and replace worn components | Lisa Chen | 2024-06-15 | Planned
2024-04-28 | Security Access Control System | Main Entrance, Building A | Low | Outdated software causing login delays | Update system firmware and improve user interface | David Park | 2024-05-15 | On Track