## Worksheet
Date | Location | Asset/Equipment | Risk Identified | Risk Level (Low/Medium/High/Critical) | Root Cause Analysis | Mitigation Strategy | Responsible Party | Due Date | Status (Open/Resolved)
2024-04-01 | Production Floor A | Motor Drive Unit #3 | Overheating during peak load | High | Insufficient cooling fan capacity in design phase. | Install additional cooling fan and upgrade heat dissipation panel. | Electrical Maintenance Team | 2024-04-15 | Open
2024-03-18 | Warehouse B | Automated Palletizer System | Prolonged downtime due to belt slippage | Medium | Belt tension not properly calibrated during installation. | Adjust tension settings and add sensor-based monitoring. | Operations Supervisor | 2024-04-05 | Open
2024-03-10 | Chemical Storage Area | Storage Tank 7 | Potential leak due to corrosion in weld joints | Critical | Welding performed without proper inspection protocol. | Replace tank section and conduct full NDT inspection. | Compliance & Safety Officer | 2024-04-10 | Open
2024-04-15 | Control Room | Main Server Rack | Faulty UPS battery backup failure after 18 months | High | Battery maintenance not scheduled per protocol. | Replace all batteries and implement automated alert system. | IT Department Manager | 2024-05-01 | Open
2024-04-03 | Roof Access Point C | Emergency Escape Ladder | Ladder rusted and structurally weak | Critical | Rust not detected during routine inspections. | Replace entire ladder with corrosion-resistant material. | Safety & Facilities Team | 2024-04-10 | Open
Multi-Page Risk Management Maintenance Log ¦ Version 2.1 ¦ Prepared for Operational Safety Compliance