## Worksheet
Date | Asset/Equipment | Risk Identified | Risk Level (Low/Med/High/Critical) | Likelihood | Impact | Mitigation Action | Responsible Person | Due Date | Status (Open/In Progress/Completed)
2024-03-15 | Server Room HVAC System | Excessive temperature during peak hours | High | Medium | High | Install additional cooling units and monitor temperature hourly. | John Smith | 2024-04-15 | Open
2024-03-20 | Production Line 3 | Motor overheating during operation | Critical | High | High | Conduct thermal inspection and replace faulty motor within 48 hours. | Anna Lee | 2024-03-25 | In Progress
2024-03-18 | Office Building Fire Extinguishers | Expiry of critical extinguishers | Medium | Low | High | Replace all expired fire extinguishers and update inventory. | Michael Chen | 2024-04-01 | Open
2024-03-25 | Network Switch Cabinet | Unsecured physical access to cabinet | Medium | Medium | Medium | Install lockable access control and log entry attempts. | Sarah Williams | 2024-04-10 | Open