## Worksheet
Date | Maintenance Activity | Risk Identified | Risk Level (Low/Medium/High) | Mitigation Strategy | Responsible Person | Status (Completed/Pending/In Review)
2024-03-15 | Quarterly inspection of HVAC system | System failure during peak usage | High | Install redundant filters and schedule preventive maintenance every 3 months | J. Smith | Completed
2024-04-10 | Electrical panel check and grounding test | Unstable voltage readings | Moderate | Replace faulty surge suppressors and conduct monthly voltage audits | K. Lee | Pending
2024-05-03 | Fault analysis of fire suppression system | Delayed response time in simulation test | High | Upgrade detection sensors and retrain staff on emergency protocols | M. Patel | In Review
2024-06-18 | Review of access control logs for security breaches | Unauthorized access detected in past quarter | Moderate | Implement two-factor authentication and conduct bi-weekly audits | S. Johnson | Completed