## Worksheet
Date | Asset/Equipment | Risk Identified | Risk Level (Low/Medium/High/Critical) | Impact Assessment | Mitigation Strategy | Responsible Party | Deadline | Status (Open/Resolved)
2024-04-01 | Production Line A | Unscheduled downtime due to overheating | High | Causes 8-hour production halt and safety hazard | Install temperature sensors and automated shutdowns | Engineering Team | 2024-04-15 | Open
2024-03-30 | Server Room HVAC System | Failure to maintain temperature control | Medium | Potential for data loss during peak usage | Upgrade to redundant cooling units with backup power | IT Operations Team | 2024-04-20 | Open
2024-04-10 | Chemical Storage Cabinet | Improper labeling and access control | Critical | High risk of accidental exposure or fire hazard | Implement barcode labeling and biometric access controls | Safety & Compliance Officer | 2024-05-01 | Resolved
2024-04-15 | Emergency Power Backup System | Insufficient runtime during outages | High | Results in loss of critical operations during grid failure | Replace backup batteries with higher-capacity units | Maintenance Supervisor | 2024-05-10 | Open