## Worksheet
Month | Risk Management Activities |  |  | Risk Assessment Frequency | Responsible Party | Action Plan
| Identification | Evaluation | Mitigation
January | Conduct initial risk inventory | Score likelihood and impact (1–5) | Develop preliminary controls | Monthly | Risk Management Team | Review and document all identified risks
February | Update risk register with new threats | Re-evaluate high-impact risks | Implement control measures for top 3 risks | Bi-monthly | Risk Management Team | Monitor effectiveness of mitigation plans
March | Perform stakeholder risk interviews | Assess operational exposure | Adjust controls based on feedback | Quarterly | Department Heads | Integrate findings into business continuity planning
April | Review cybersecurity risk posture | Evaluate data breach probability | Upgrade access controls and logging | Quarterly | IT Security Team | Conduct penetration test if required
May | Evaluate supply chain vulnerabilities | Map dependencies and exposure points | Establish backup suppliers for critical components | Quarterly | Procurement & Operations | Document risk response strategies
June | Review environmental and compliance risks | Assess regulatory alignment | Update policy documentation and training | Quarterly | Legal & Compliance Team | Schedule audit readiness checks
July | Evaluate market and economic risks | Forecast downturn scenarios | Develop contingency financial plans | Quarterly | Finance Department | Integrate into strategic planning cycle
August | Assess internal process risks (e.g., audit gaps) | Identify root causes of deviations | Revise SOPs and training modules | Quarterly | Internal Audit Team | Establish corrective action tracking system
September | Conduct cross-departmental risk workshop | Align on enterprise-wide risks | Create joint mitigation protocols | Quarterly | Executive Management | Present findings to board-level review
October | Evaluate emerging threats (e.g., AI, cybercrime) | Benchmark against industry standards | Deploy threat intelligence monitoring tools | Quarterly | Risk & Innovation Office | Update risk dashboard and alert systems
November | Review annual risk performance metrics | Compare actual vs. predicted outcomes | Adjust risk appetite and thresholds | Annual review | Risk Committee | Refine annual risk management plan
December | Finalize and archive year-end risk report | Summarize key achievements and gaps | Plan next year’s risk management initiatives | Annual review | CEO & CFO | Present to executive leadership and board