## Worksheet
Date | Risk Identified | Potential Impact | Likelihood | Mitigation Strategy | Responsible Party | Status
01/04/2024 | Data breach due to outdated software | High - Loss of sensitive client data | Medium | Apply patch updates and conduct regular security audits | IT Security Team | Active
02/04/2024 | Vendor failure to meet SLA | Moderate - Delayed project delivery | High | Establish backup vendor and monitor performance KPIs | Project Manager | Monitoring
03/04/2024 | Compliance gap in regulatory reporting | High - Legal penalties and reputational damage | Medium | Conduct compliance training and update reporting workflows | Legal & Compliance Officer | <Planned Action
04/04/2024 | Staff turnover leading to knowledge loss | Moderate - Disruption in operations | High | Implement documentation and cross-training programs | HR & Operations Team | In Progress