## Worksheet
Month | Risk Category | Risk Identified | Likelihood (1-5) | Impact (1-5) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Deadline | Status
January | Operational Risk | Equipment failure in production line | 4 | 5 | 20 | Regular maintenance schedule and preventive checks | Operations Manager | March 31, 2024 | Active
January | Compliance Risk | Non-compliance with new data privacy regulations | 3 | 4 | 12 | Update internal policy documents and employee training | Legal & Compliance Officer | February 15, 2024 | Planned
February | Financial Risk | Supply chain cost inflation | 5 | 4 | 20 | Negotiate long-term contracts with alternative suppliers | Procurement Director | April 30, 2024 | Active
February | Reputational Risk | Customer data breach incident | 5 | 5 | 25 | Enhance cybersecurity protocols and conduct post-incident review | CISO (Chief Information Security Officer) | March 10, 2024 | Monitoring
March | Market Risk | Sudden decline in market demand | 4 | 5 | 20 | Launch targeted marketing campaigns and product diversification plan | Marketing Head | May 15, 2024 | Planning