## Worksheet
Month | Risk Identification | Likelihood | Impact | Risk Score (L×I) | Mitigation Strategy | Responsible Party | Timeline | Status
January | Supply Chain Disruption | Medium | High | 6 | Diversify suppliers; maintain safety stock | Operations Manager | Q1 2024 | Pending Review
January | Data Breach | High | Very High | 12 | Implement multi-factor authentication and encryption | Cybersecurity Lead | Immediate to Q2 2024 | In Progress
January | Regulatory Non-Compliance | Low | High | 3 | Conduct quarterly compliance audits | Legal Officer | Ongoing | On Track
February | Key Personnel Departure | Medium | Medium | 6 | Develop knowledge transfer plan and succession strategy | HRC Director | Q2 2024 | Pending Approval
February | Technology Obsolescence | High | Medium | 10 | Schedule technology refresh cycle every 3 years | IT Director | Ongoing Review | Planned