## Worksheet
Month | Risk Identification | Likelihood (1-5) | Impact (1-5) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Monitoring Frequency
January | Project scope creep | 4 | 5 | 20 | Define clear change control process and obtain approval for all changes. | Project Manager | Monthly
February | Key team member turnover | 3 | 4 | 12 | Implement backup staffing plan and conduct regular staff retention reviews. | HR Director | Quarterly
March | Delays in vendor delivery | 5 | 3 | 15 | Establish dual sourcing strategy and build buffer time into the schedule. | Procurement Lead | Bi-weekly
April | Security breach in data systems | 2 | 5 | 10 | Enhance firewall protocols and conduct penetration testing every quarter. | CISO | Quarterly
May | Client budget reduction | 4 | 4 | 16 | Propose phased deliverables and renegotiate scope based on client feedback. | Project Manager | Monthly