## Worksheet
Month | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Responsible Party | Timeline | Budget Allocation (USD)
January | Supply chain disruption | High likelihood, High impact | Establish dual sourcing agreements with regional suppliers | Procurement Director | Q1 - Q2 2024 | $50,000
February | Data breach due to outdated systems | Medium likelihood, High impact | Implement endpoint encryption and conduct quarterly penetration tests | CISO & IT Lead | Monthly from February 2024 onward | $75,000
March | Regulatory non-compliance risk | Low likelihood, High impact | Conduct annual compliance audit and update policy framework | Legal & Compliance Officer | March 2024 - June 2024 | $30,000
April | Key personnel turnover | High likelihood, Medium impact | Develop succession planning and employee engagement initiatives | HR Director | Ongoing from April 2024 | $25,000
May | Third-party vendor failure | Medium likelihood, Medium impact | Review and re-evaluate vendor contracts; include SLAs and exit clauses | Procurement & Risk Manager | Q2 2024 | $40,000
June | Market volatility affecting pricing | High likelihood, Medium impact | Introduce dynamic pricing models and hedging instruments | Finance & Strategy Lead | Q3 2024 onwards | $60,000