## Worksheet
Month | Risk Category | Risk Identified | Likelihood (1-5) | Impact (1-5) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Team Member | Due Date | Status
January | Operational Risk | Supply chain disruption due to logistics delays | 3 | 4 | 12 | Establish alternative suppliers and diversify logistics routes | Logistics Team | February 5, 2024 | In Progress
January | Financial Risk | Fluctuating exchange rates affecting international revenue | 4 | 3 | 12 | Implement hedging strategies and dynamic currency forecasting | Finance Team | February 10, 2024 | Planned
January | Compliance Risk | Regulatory changes in data privacy laws | 2 | 5 | 10 | Conduct compliance training and update internal policies | Legal & Compliance Team | February 20, 2024 | Pending Review
January | Technology Risk | System outage due to outdated server infrastructure | 5 | 4 | 20 | Upgrade servers and implement redundancy protocols | IT Team | March 1, 2024 | High Priority
January | Reputational Risk | Negative customer feedback leading to brand damage | 3 | 5 | 15 | Improve customer service response and launch a PR campaign | Customer Experience Team | February 25, 2024 | Planned