## Worksheet
Week | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Responsible Party | Due Date | Status
Week 1 | Supply chain disruption | High likelihood, High impact | Establish dual sourcing agreements | Procurement Manager | 2023-10-08 | Pending
Week 2 | Data breach vulnerability | Medium likelihood, High impact | Enhance firewall and access controls | IT Security Lead | 2023-10-15 | In Progress
Week 3 | Regulatory compliance lapse | Low likelihood, High impact | Conduct quarterly compliance audits | Compliance Officer | 2023-10-22 | Pending
Week 4 | Project scope creep | High likelihood, Medium impact | Implement change control board (CCB) | Project Manager | 2023-10-29 | Planned