## Worksheet
Date | Risk Identified | Risk Level | Impact | Probability | Mitigation Strategy | Owner | Status
2023-10-01 | Server downtime due to hardware failure | High | Severe | Medium | Implement redundant servers and scheduled maintenance checks. | Jane Doe | Pending Review
2023-10-02 | Third-party vendor data breach risk | Medium | <HighModerate | Conduct vendor security audit and enforce SLAs. | John Smith | On Track
2023-10-03 | Supply chain delay impact on delivery | Low | Moderate | Low | Diversify suppliers and maintain buffer stock. | Lisa Chen | Completed