## Worksheet
Month | Risk Category | Risk Identification & Assessment |  |  |  | Mitigation Actions |  |  | Owner | Status
|  | Risk Name | Likelihood | Impact | Priority | Action Plan | Timeline | Responsible Team
January | Operational Risk | Supply Chain Disruption | Medium | High | High | Critical - Review supplier contracts | Q1 2024 | Procurement Team | Active
January | Financial Risk | Currency Fluctuation | Low | Medium | Medium | Monitor exchange rates; adjust hedging strategy | Monthly Review | Finance Department | Planned
February | Technology Risk | Data Breach Vulnerability | High | High | Critical | Conduct security audit; implement MFA rollout | Q2 2024 | IT Security Team | Pending Review
February | Compliance Risk | Regulatory Change Impact | Medium | High | High | Update compliance documentation; engage legal advisors | March 2024 | Legal & Compliance Team | On Track
March | Market Risk | Consumer Demand Shift | Medium | Medium | Medium | Analyze market trends; adjust product mix | Quarterly Review | Marketing & Sales Team | In Progress
Total Risks Identified: 6 | [9 empty] | Monthly Risk Review Scheduled