## Worksheet
Month | Risk Category | Risk Description | Likelihood (1-5) | Impact (1-5)/th> | Current Control Measures | Risk Rating (Likelihood × Impact) | Owner | Mitigation Plan | Due Date | Status
January | Operational Risk | Equipment failure due to aging infrastructure. | 4 | 5 | Regular maintenance schedule, inspection logs. | 20 | Maintenance Team Lead | Replace critical components by Q2. | 31/03/2024 | Planned
January | Financial Risk | Cash flow shortage due to delayed payments. | 3 | 4 | Cash forecasting model, early invoicing. | 12 | Finance Manager | Negotiate payment terms with key clients. | 28/02/2024 | In Progress
January | Reputational Risk | Negative media coverage due to data breach. | 5 | 5 | Data security protocols, incident response team. | 25 | CISO & PR Lead | Conduct breach simulation and public communication plan. | 01/04/2024 | Pending
February | Supply Chain Risk | Vendor delays due to geopolitical instability. | 4 | 4 | Diversified supplier base, safety stock. | 16 | Procurement Director | Identify alternative suppliers by March. | 20/03/2024 | Not Started
February | Compliance Risk | Regulatory changes may require new reporting formats. | 2 | 3 | Quarterly compliance review, legal updates. | 6 | Legal Counsel | Monitor regulatory announcements and adjust policies. | 30/04/2024 | Planned
March | Technology Risk | Outage of cloud-based systems due to vendor failure. | 5 | 4 | Redundant servers, failover mechanism. | 20 | IT Manager | Upgrade to multi-cloud architecture by May. | 15/05/2024 | Pending