## Worksheet
Month | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Responsible Party | Deadline | Status
January | Cybersecurity breach due to outdated software | High Likelihood, High Impact | Patch all critical systems; conduct quarterly audits | IT Security Team | March 31, 2024 | In Progress
February | Supply chain disruption from key vendor failure | Medium Likelihood, High Impact | Diversify vendor base; establish backup suppliers | Procurement & Operations | April 15, 2024 | Planned
March | Data privacy violation in employee onboarding process | Low Likelihood, Medium Impact | Implement mandatory training; update consent forms | HR & Compliance | April 30, 2024 | Pending Review
April | Regulatory non-compliance due to policy lag | High Likelihood, High Impact | Conduct compliance gap analysis; update policies quarterly | Legal & Risk Management Office | May 31, 2024 | In Review
May | Market volatility affecting revenue projections | Medium Likelihood, Medium Impact | Develop flexible pricing models; monitor macroeconomic indicators | Finance & Strategy | June 10, 2024 | Planned
June | Employee turnover leading to knowledge loss | Medium Likelihood, Medium Impact | Implement onboarding documentation; create knowledge base | HR & IT Support | July 15, 2024 | Scheduled
July | Natural disaster impact on data centers | Low Likelihood, High Impact | Establish off-site backup data centers; perform disaster drills | IT Infrastructure Team | August 30, 2024 | Not Started
August | Third-party software compliance failure | Medium Likelihood, High Impact | Conduct vendor audits; enforce contract compliance clauses | Legal & Compliance Office | September 15, 2024 | Planned
September | Project scope creep leading to budget overruns | High Likelihood, Medium Impact | Implement change control board; define clear approval thresholds | Project Management Office | October 31, 2024 | In Development
October | Rise in phishing attacks targeting executives | High Likelihood, High Impact | Deploy multi-factor authentication; conduct executive awareness training | Cybersecurity & HR | November 10, 2024 | Upcoming
November | Loss of key client due to poor service delivery | Medium Likelihood, High Impact | Improve SLAs; establish client feedback loops | Customer Success & Operations | December 15, 2024 | Planned
December | New legislation affecting data handling practices | High Likelihood, High Impact | Establish cross-functional legal and compliance task force | Legal & Risk Management Office | January 31, 2025 | On Hold