## Worksheet
Month | Risk Category | Risk Description | Likelihood (1-5) | Impact (1-5) th> | Risk Score | Mitigation Strategy | Owner | Due Date | Status
January | Operational Risk | Power outage affecting data centers | 4 | 5 | 20 | Install backup generators and redundant systems | IT Infrastructure Team | 2024-01-31 | In Progress
February | Financial Risk | Fluctuation in supplier pricing | 3 | 4 | 12 | Negotiate long-term contracts and diversify suppliers | Procurement Department | <2024-02-28 | Planned
March | Compliance Risk | Regulatory change in data privacy laws | 5 | 5 | 25 | Conduct legal review and update policies immediately | Legal & Compliance Team | 2024-03-31 | Pending
April | Technology Risk | System downtime due to software bugs | 4 | 4 | 16 | Implement automated testing and CI/CD pipelines | Engineering Team | 2024-04-30 | Planned
May | Reputational Risk | <Customer data breach incident | 5 | 5 | 25 | Enhance cybersecurity and conduct employee training | Security & Risk Management Office | 2024-05-31 | At Risk
Total Risk Score (Sum of all risk scores): |  |  |  |  | 108 | Monthly Review Date: