## Worksheet
Monthly Risk Management Planner - Planning View
Date | Risk ID | Risk Description | Category | Impact Level (Low/Med/High/Critical) | Probability (Low/Med/High) | Owner | Status (Open/In Review/Resolved) | Action Plan | Due Date | Last Reviewed Date
01-Apr-2024 | RISK-001 | Data breach due to outdated software. | Security | High | High | J. Smith | Open | Update firewall and patch legacy systems. | 30-Apr-2024
05-Apr-2024 | RISK-002Faulty supply chain delivery. | Operations | Medium | Moderate | L. Chen | In Review | Identify backup suppliers and evaluate contracts. | 15-Apr-2024 | 01-Apr-2024
10-Apr-2024 | RISK-003Employee turnover in IT department. | Human Resources | Medium | Moderate | M. Garcia | Open | Implement retention program and offer training. | 25-Apr-2024
15-Apr-2024 | RISK-004Server outage during peak traffic. | IT Infrastructure | High | High | K. Patel | In Review | Deploy redundant servers and load balancing. | 30-Apr-2024 | 05-Apr-2024
20-Apr-2024 | RISK-005Cyberattack via phishing emails.Security | High | Moderate | A. Johnson | Open | Conduct employee training and update email filters. | 25-Apr-2024
25-Apr-2024 | RISK-006Labor shortage in manufacturing.Operations | Medium | Moderate | T. Williams | Open | Negotiate flexible work hours and recruit temp staff. | 30-Apr-2024
30-Apr-2024 | RISK-007Regulatory change affecting compliance.Compliance | Critical | Moderate | S. Lee | In Review | Review policies, consult legal team, update reporting. | 15-May-2024 | 01-Apr-2024
05-May-2024 | RISK-008Potential vendor financial instability.Risk Management | Medium | High | C. Brown | Open | Diversify vendor base and conduct financial audits. | 20-May-2024
10-May-2024 | RISK-009New market entry with uncertain demand.Market Risk | High | Moderate | D. Taylor | In Review | Run pilot test and conduct customer surveys. | 25-May-2024
15-May-2024 | RISK-010Funding delays from investors.Funding | Medium | High | E. Martinez | Open | Negotiate revised timelines and secure contingency funds. | 30-May-2024
20-May-2024 | RISK-011Key software license expiration.Technology | Moderate | High | F. Rivera | In Review | Purchase extension or migrate to open-source alternative. | 30-May-2024
25-May-2024 | RISK-012Supply chain disruption due to natural events.Risk Management | Critical | High | G. White | Open | Create emergency supply chain protocol and stock buffer. | 30-May-2024
30-May-2024 | RISK-013Data privacy violation due to misconfigured cloud settings.Security | High | Moderate | H. Kim | In Review | Conduct audit, update access controls, and implement monitoring. | 15-Jun-2024
05-Jun-2024 | RISK-014Inadequate customer support during peak periods.Customer Service | Moderate | High | I. Adams | Open | Hire additional support staff and automate responses. | 20-Jun-2024
10-Jun-2024 | RISK-015Fall in product quality due to raw material issues.Operations | High | Moderate | J. Clark | In Review | Switch suppliers and implement quality checks. | 25-Jun-2024
15-Jun-2024 | RISK-016Loss of key client due to poor service delivery.Customer Retention | Critical | Moderate | K. Singh | Open | Review service performance and improve SLAs. | 30-Jun-2024
20-Jun-2024 | RISK-017Cybersecurity breach in third-party system integration.Security< | Critical | High | L. Foster | In Review | Terminate connection, assess vulnerabilities, reconfigure access. | 30-Jun-2024
25-Jun-2024 | RISK-018Limited scalability of current platform architecture.Technology | Moderate | High | M. Hughes | Open | Begin architectural review and plan upgrade roadmap. | 30-Jun-2024
30-Jun-2024 | RISK-019Rising operational costs due to inflation.Finance | Medium | Moderate | N. Perez | In Review | Conduct cost-benefit analysis and explore automation. | 15-Jul-2024
05-Jul-2024 | RISK-020Potential data loss from unencrypted backups.Security | High | Moderate | O. Reynolds | Open | Encrypt all backup files and verify recovery procedures. | 20-Jul-2024
10-Jul-2024 | RISK-021New regulatory requirements on data handling.Compliance | Critical | Moderate | P. Grant | In Review | Update policies and conduct staff training. | 30-Jul-2024
15-Jul-2024 | RISK-022Sudden increase in customer complaints.Customer Service | Moderate | High | Q. Scott | Open | Analyze root cause and improve response times. | 30-Jul-2024
20-Jul-2024 | RISK-023Faulty product recall due to design flaw.Product Quality | Critical | Moderate | R. Turner | In Review | Initiate recall, conduct root cause analysis, revise design. | 30-Jul-2024
25-Jul-2024 | RISK-024Labor unrest in production facilities.Operations | Medium | High | S. Evans | Open | Promote communication forums and offer incentives. | 31-Jul-2024
30-Jul-2024 | RISK-025Inadequate cybersecurity incident response plan.Security | Critical | Moderate | T. Clark | In Review | Develop and simulate a full incident response plan. | 15-Aug-2024
05-Aug-2024 | RISK-026Potential legal liability from product liability claims.Compliance | Moderate | High | U. Foster | Open | Review insurance coverage and legal documentation. | 20-Aug-2024
10-Aug-2024 | RISK-027Loss of key partner due to contract disputes.Relationship Management< | Moderate | High | V. Whitehead | In Review | Negotiate amicable resolution and evaluate alternatives. | 25-Aug-2024
15-Aug-2024 | RISK-028Failing to meet key performance indicators (KPIs).Performance | High | Moderate | W. Morris | In Review | Analyze metrics, revise goals, and reallocate resources. | 30-Aug-2024
20-Aug-2024 | RISK-029Outdated cybersecurity protocols.Security | Critical | Moderate | X. HillIn Review
25-Aug-2024
30-Aug-2024
05-Sep-2024
10-Sep-2024
15-Sep-2024
20-Sep-2024
25-Sep-2024
30-Sep-2024
05-Oct-2024
10-Oct-2024
15-Oct-2024
20-Oct-2024
25-Oct-2024
30-Oct-2024
05-Nov-2024
10-Nov-2024
15-Nov-2024
20-Nov-2024
25-Nov-2024
30-Nov-2024
05-Dec-2024
10-Dec-2024
15-Dec-2024
20-Dec-2024
25-Dec-2024
30-Dec-2024
RISK-055
This template is designed for monthly risk management planning. Use it in Excel or export as CSV to manage risks effectively across departments and timeframes.