## Worksheet
Month | Risk Assessment & Mitigation Plan |  |  |  | Status
| Identified Risks | Mitigation Strategies | Responsible Party | Deadline
January | Supply chain delays | Establish dual suppliers; monitor lead times | Procurement Manager | 2024-01-31 | Active
January | Data breach vulnerability | Enhance firewalls; conduct monthly audits | IT Security Team | 2024-01-30 | Active
February | Key employee turnover | Implement retention program; offer career development | HR Department | 2024-02-28 | Planning
February | Regulatory changes | Monitor compliance updates; schedule review meetings | Legal & Compliance | 2024-03-15 | Pending
March | Project scope creep | Enforce change control process; conduct monthly reviews | Project Manager | 2024-03-31 | Active
March | External vendor failure | Conduct vendor performance reviews; identify backup options | Operations Team | 2024-04-15 | Planning
Risk Management Monthly Planner – Printable Version |  |  |  |  | Approved by: ________________________