## Worksheet
Month | Risk Category | Risk Identification | Likelihood | Impact> | Risk Score (L×I) | Mitigation Strategy | Responsible Party | Due Date | Status
January | Operational | Supply chain disruption | Medium | High | 6 | Diversify suppliers and establish backup contracts | Procurement Team | 2024-01-15 | Planned
January | Financial | Cash flow shortage | High | Medium | 12 | Adjust payment terms and secure short-term financing | Finance Manager | 2024-01-30 | Pending
February | Technology | Data breach vulnerability | High | High | 18 | Implement advanced encryption and conduct regular audits | IT Security Team | 2024-02-28 | In Progress
March | Compliance | Regulatory change risk | Medium | High | 12 | Monitor regulatory updates and update policies accordingly | Legal Department | 2024-03-10 | Not Started
Total Risk Score: |  |  |  |  | 58 | Review & Update Monthly