## Worksheet
Order ID | Risk Assessment Date | Risk Level | Risk Description | Mitigation Strategy | Responsible Party | Status | Next Review Date
RISK-2024-001 | 2024-03-15 | High | Data breach risk due to outdated software. | Implement encryption and software patching protocol. | IT Security Team | Active | 2024-06-15
RISK-2024-002 | 2024-03-10 | Medium | Vendor dependency on single supplier. | Diversify suppliers and establish SLAs. | Procurement Office | Pending Action | 2024-05-10
RISK-2024-003 | 2024-03-20 | Low | Potential compliance gap in reporting. | Update internal documentation and training. | Compliance Officer | Completed | 2024-09-20
RISK-2024-004 | 2024-03-18 | High | Cyberattack from unknown IP addresses. | Deploy firewall updates and intrusion detection system. | Network Security Team | Under Review | 2024-04-18