## Worksheet
Risk Identifier | Risk Description | Likelihood | Impact | Risk Score (L x I) | Mitigation Strategy | Responsible Party | Due Date | Status
R-001 | System outage due to hardware failure | High | Critical | 9 | Implement redundant servers and regular failover testing | IT Operations Team | 2024-03-15 | In Progress
R-002 | Third-party vendor data breach | Medium | High | 6 | Conduct annual security audits and strengthen contract clauses | Security Office | 2024-06-30 | Planned
R-003 | Regulatory non-compliance due to policy gap | Low | High | 3 | Update compliance policy and conduct training sessions | Legal & Compliance Team | 2024-09-10 | Pending Review
R-004 | Supply chain disruption from global events | High | Medium | 6 | Establish alternate suppliers and diversify sourcing | Procurement Team | 2024-05-20 | Completed
R-005 | Employee fraud or internal misuse of data | Medium | Critical | 7 | Enforce access controls, audit logs, and staff awareness programs | HR & Security Team | 2024-12-01 | Not Started