## Worksheet
Order ID | Risk Assessment Date | Risk Category | Risk Level | Likelihood | Impact | Current Mitigation Strategy | Owner (Name) | Status | Next Review Date | Comments
RM-001 | 2024-03-15 | Operational Risk | High | Moderate | Critical | Additional staff training and dual authorization protocol | Jane Smith | Active | 2024-06-15 | System vulnerabilities identified during audit; controls being updated.
RM-002 | 2024-04-10 | Compliance Risk | Moderate | Low | High | Enhanced documentation and quarterly compliance audits | Michael Lee | Pending Review | 2024-05-10 | New regulatory requirement introduced; alignment in progress.
RM-003 | 2024-03-22 | Financial Risk | Low | High | Critical | Diversification of suppliers and hedging instruments deployed | Sarah Chen | Resolved | 2024-05-01 | No further exposure observed post-intervention.
RM-004 | 2024-05-03 | Data Breach Risk | High | Moderate | Critical | Access controls tightened; multi-factor authentication enforced | David Patel | Active Monitoring | 2024-08-03 | No breaches reported since implementation.