## Worksheet
Risk Management Order Tracker - Manager View
Order ID | Request Date | Asset/Project | Risk Type | Risk Level | Description th> | Status th> | Assigned To th> | Action Required th> | Last Updated th>
RISK-2024-001 | 2024-03-15 | Cloud Infrastructure Upgrade | Data Breach | High | Unencrypted data exposure during migration. | In Progress | Jane Smith | Implement encryption and conduct penetration test. | 2024-03-20
RISK-2024-002 | 2024-03-18 | Supply Chain Integration | Supplier Failure | Moderate | Single-source dependency on vendor A. | Pending Review | John Doe | Identify backup suppliers and diversify contracts. | 2024-03-19
RISK-2024-003 | 2024-03-19 | New Product Launch | Market Disruption | High | Competitor may launch similar product in Q2. | Open | Sarah Lee | Conduct competitive analysis and adjust go-to-market plan. | 2024-03-19
RISK-2024-004 | 2024-03-21 | Data Center Migration | Service Downtime | Critical | Failure during transition may affect 5,000 users. | On Hold | Mike Brown | Perform failover testing and approve backup plan. | 2024-03-22