## Worksheet
Page | Section | Risk Factor | Likelihood | Impact | Risk Rating | Mitigation Strategy | Responsible Party | Review Date
1 | Payroll Processing | Data Entry Error | Medium | High | High | Implement dual verification system for payroll entries. | HR Supervisor | 2024-05-15
1 | Payroll Processing | Late Payment | Low | Medium | Medium | Set up automated payroll release alerts and daily monitoring. | Finance Manager | 2024-05-16
2 | Payroll Reporting | System Downtime | High | High | Critical | Backup server and off-site cloud replication with failover protocol. | IT Director | 2024-05-20
2 | Payroll Reporting | Report Inaccuracy | Medium | High | High | Conduct monthly audit of payroll reports and reconciliation. | Audit Committee | 2024-06-01
3 | Payroll Compliance | Regulatory Change | Medium | High | High | Assign legal team to monitor updates and update payroll policies quarterly. | Legal Officer | 2024-06-15
3 | Payroll Compliance | Tax Misclassification | High | Critical | Critical | Implement mandatory employee classification review before payroll run. | HR Manager | 2024-05-30