## Worksheet
Risk Identification | Risk Description | Likelihood | Impact> | Risk Rating | Mitigation Strategy | Responsible Party | Review Date
Payroll Data Breach | Unauthorized access to employee salary and personal information. | High | Critical | Severe | Implement end-to-end encryption and multi-factor authentication. | IT Security Team | 2024-06-30
Late Payroll Processing | Delay in salary disbursement due to system failure or manual error. | Medium | High | Moderate-High | Automate payroll schedule with backup processing protocols. | Finance Operations Manager | 2024-07-15
Compliance Violation | Failure to meet local or federal payroll tax regulations. | Medium | High | High | Conduct quarterly compliance audits and train staff on regulations. | Legal & Compliance Officer | 2024-08-20
Payroll System Outage | Complete downtime of payroll processing system. | High | Critical | Severe | Deploy redundant systems with failover capability and 24/7 monitoring. | IT Infrastructure Team | 2024-09-10