## Worksheet
Risk Identification | Risk Description | Likelihood | Impact th> | Risk Score (L×I) | Mitigation Strategy | Responsible Party | Timeline | Status
R-001 | System outage due to hardware failure | High | Critical | 9 | Redundant servers and automatic failover | IT Infrastructure Team | Q1 2024 | Active
R-002 | Data breach from unsecured endpoints | Medium | High | <6 | Endpoint encryption and user awareness training | Security Operations Team | Ongoing | In Progress
R-003 | Regulatory non-compliance due to delayed reporting | Low | High | 3 | Automated reporting schedule and compliance dashboard | Legal & Compliance Office | Q2 2024 | Planned
R-004 | Vendor failure to meet SLAs | Medium | Medium | 4 | Vendor performance review and backup providers | Procurement & Operations | Q3 2024 | Pending Review
R-005 | Natural disaster impacting data centers | Low | Critical | 2 | Geographic redundancy and disaster recovery plan | Disaster Recovery Team | Annual Review | Approved
Total Risk Score: |  |  |  |  | 35 | Prepared by Risk Management Office