## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Rating | Mitigation Strategy | Responsible Party | Due Date | Status
1 | Loss of key vendor services due to contract expiration | Medium | High | High | Negotiate renewal terms; identify backup vendors | Operations Manager | 2024-03-30 | Open
2 | Data breach due to outdated software | High | Critical | Critical | Conduct security audit; update software & implement patches | CISO | 2024-04-15 | In Progress
3 | Market demand decline affecting sales projections | Medium | High | High | Conduct market research; diversify product offerings | Marketing Director | 2024-05-20 | Planned
4 | Cyber attack on internal network | High | Critical | Critical | Deploy firewalls, conduct employee training, and enhance monitoring | IT Security Team | 2024-03-15 | Completed
5 | Supply chain disruption due to natural disaster | Low | High | Medium | Establish alternative suppliers; develop contingency inventory plan | Logistics Manager | 2024-06-10 | Open