## Worksheet
Risk Identification | Risk Description | Likelihood | Impact(th) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Timeline | Status | Review Date
1 | System outage due to server failure | High | Critical | 9 | Implement redundant servers and automated failover | IT Operations Team | Q1 2024 | Open | 05/15/2024
2 | Data breach due to unpatched software | Medium | High | <6 | Establish patch management policy and regular audits | Security Team | Ongoing | In Progress | 06/01/2024
3 | Regulatory non-compliance due to policy gap | Low | High | 3 | Conduct compliance gap analysis and update policies | Legal & Compliance Officer | Q2 2024 | Planned | 07/10/2024
4 | Supply chain disruption from vendor failure | Medium | Medium | 4 | Diversify vendor base and establish backup suppliers | Procurement Team | Q3 2024 | Open | 08/15/2024
5 | Employee data misuse due to inadequate training | Low | Medium | 2 | Implement mandatory data handling training annually | HR & Training Department | Q4 2024 | Planned | 10/01/2024