## Worksheet
Date | Risk Identified | Impact Level | Likelihood | Risk Score (Impact × Likelihood) | Mitigation Plan | Responsible Employee | Status
2024-04-01 | Data Breach due to Unsecured Endpoint | High | Medium | 6 | Implement endpoint encryption and access controls. | J. Smith | Pending Review
2024-04-05 | Server Outage from Backup Failure | High | Low | 3 | Schedule weekly backup integrity checks and redundancy testing. | A. Johnson | In Progress
2024-04-10 | Third-party Vendor Misconduct | Moderate | High | 6 | Review vendor contract terms and conduct quarterly audits. | L. Brown | Pending Approval
2024-04-15 | Incorrect Access Permissions | Low | Medium | 3 | Conduct role-based access review every quarter. | M. Davis | Completed