## Worksheet
Date | Risk Identified | Impact Level | Likelihood | Risk Rating (Impact × Likelihood) | Mitigation Strategy | Responsible Party | Due Date | Status
2024-04-01 | Data breach due to unpatched systems | High | Medium | 6 | Apply patches and deploy endpoint detection tools | IT Security Team | 2024-04-15 | Pending
2024-04-05 | Vendor supply chain failure | Moderate | High | 6 | Establish dual sourcing and backup vendors | Procurement Manager | 2024-04-30 | In Progress
2024-04-10 | Employee phishing susceptibility | Medium | High | 6 | Conduct training sessions and enable email filters | HR & Training Dept. | 2024-04-25 | Planned
2024-04-15 | Server outage due to power failure | High | Medium | 6 | Install backup generators and UPS systems | Facilities Team | 2024-05-01 | Pending Approval