## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Rating | Mitigation Strategy | Owner | Due Date | Status
R001 | System downtime due to server failure | IT Infrastructure | High | Critical | High | Implement redundant servers and regular failover testing | IT Manager | 2024-04-30 | Active
R002 | Data breach from unauthorized access | Security | Medium | High | High | Deploy multi-factor authentication and conduct bi-annual penetration tests | Security Officer | 2024-05-15 | Planned
R003 | Compliance failure with GDPR regulations | Legal & Compliance | Low | High | Medium | Conduct quarterly compliance audits and staff training sessions | Compliance Director | 2024-06-30 | Pending Review
R004 | Supply chain disruption due to vendor failure | Operations | Medium | Medium | Medium | Establish backup vendors and diversify supplier base | Operations Lead | 2024-03-15 | Completed
R005 | Cyberattack from phishing campaign | Security | High | Critical | High | Enhance email filtering and run employee awareness programs | HR & Security Team | 2024-07-05 | Active