## Worksheet
Date | Risk Identifier | Risk Description | Likelihood | Impact | Risk Rating (L x I) | Mitigation Strategy | Responsible Person | Deadline | Status
2023-10-05 | RISK-001 | Key client contract delay due to vendor failure. | High | High | 9 (High) | Identify backup vendors and initiate transition plan. | Sarah Chen | 2023-10-15 | Active
2023-10-06 | RISK-002 | Data breach due to outdated security protocols. | Medium | Critical | 6 (High) | Conduct security audit and apply patch updates. | Michael Lee | 2023-10-12 | Pending Review
2023-10-08 | RISK-003 | Team member turnover leading to project delays. | Low | Medium | 3 (Medium) | Enhance onboarding and cross-train team members. | Linda Park | 2023-10-20 | Planned
2023-10-10 | RISK-004 | Supply chain disruption due to transportation issues. | High | Medium | 6 (High) | Diversify suppliers and establish buffer inventory. | David Wong | 2023-10-25 | In Progress