## Worksheet
Risk Item | Risk Level | Likelihood | Impact> | Assigned To | Due Date | Mitigation Plan | Status
System Downtime | High | Medium | High | IT Operations Team | 2024-04-15 | Backup servers in place; failover protocol active. | In Progress
Data Breach | Critical | High | <Critical | Cybersecurity Team | 2024-04-10 | Multi-factor authentication enforced; audit logs increased. | Planned
Regulatory Non-Compliance | Medium | Low | High | Legal & Compliance Office | 2024-05-01 | Quarterly audit schedule; policy updates implemented. | Pending Review
Third-Party Vendor Risk | Medium | Medium | Medium | Procurement Team | 2024-04-25 | Vendor risk assessment completed; contract clauses reviewed. | Completed