## Worksheet
Date | Risk Identified | Risk Level | Potential Impact | Mitigation Strategy | Responsible Party | Status | Next Review Date
2024-04-01 | Supply chain disruption | High | Financial loss, delays | Diversify suppliers; establish backup agreements | Procurement Team | Active | 2024-04-15
2024-04-02 | Cybersecurity breach | Critical | Data loss, reputational damage | Implement multi-factor authentication; conduct regular audits | IT Security Team | Pending | 2024-04-10
2024-04-03 | Regulatory change | Medium | Compliance penalties | Monitor updates; update compliance protocols monthly | Legal Department | Planned | 2024-04-20
2024-04-04 | Employee turnover | Low | Knowledge gap, operational delay | Enhance onboarding; implement mentorship program | HR Department | Active | 2024-04-25