## Worksheet
Date | Risk Identified | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy | Responsible Party | Status
2024-04-01 | Client data breach due to outdated software | 5 | 5 | 25 | Implement patch updates and conduct security audits quarterly. | IT Department | Active
2024-04-05 | Project scope creep due to lack of clear deliverables | 4 | 4 | 16 | Establish a formal change control process and require sign-off on scope changes. | Project Manager | Pending Review
2024-04-10 | Vendor financial instability | <3 | 5 | 15 | Conduct annual vendor financial reviews and diversify service providers. | Procurement Team | Under Review
2024-04-15 | Compliance failure due to missing documentation | 5 | 4 | 20 | Implement automated compliance tracking and assign documentation owners. | Legal & Compliance Office | Action Required