## Worksheet
Date | Risk Identified | Risk Assessment |  |  | Mitigation Strategy | Responsible Party | Status
|  | Likelihood | Impact th> | Priority
2024-04-01 | Data Breach Due to Weak Passwords | Medium | High | High | Implement multi-factor authentication and password policy enforcement | Jane Doe | Open
2024-04-05 | Server Downtime During Peak Hours | High | <Medium | High | Add load balancers and scheduled maintenance windows | John Smith | In Progress
2024-04-10 | Third-Party Vendor Mismanagement | Medium | Medium | Medium | Conduct vendor audits and require SLAs | Alice Johnson | Planned
2024-04-15 | Insufficient Backup Procedures | Low | High | High | Automate daily backups with off-site storage | Bob Wilson | Pending Review