## Worksheet
Date | Risk Identified | Impact Level | Likelihood | Mitigation Strategy | Responsible Person | Status
2024-04-01 | Data Breach Due to Poor Access Controls | High | Medium | Implement role-based access and multi-factor authentication | Alex Morgan | In Progress
2024-04-05 | Vendor Dependency Risk | Medium | High | Establish vendor risk assessment framework and backup options | Jordan Lee | Planned
2024-04-10 | Cyber Attack on Cloud Infrastructure | High | High | Deploy enhanced intrusion detection and regular penetration testing | Samira Patel | Active
2024-04-15 | Compliance Gap in Regulatory Reporting | Medium | Low | Update reporting workflows and automate compliance checks | Taylor Reed | Completed