## Worksheet
Date | Risk Identified | Risk Level | Potential Impact | Likelihood | Owner/Team | Mitigation Plan | Status | Next Review Date
2024-04-05 | Supply chain disruption | High | Critical | Medium | Operations Team | Diversify suppliers; establish backup vendors | Active | 2024-05-05
2024-04-10 | Data breach vulnerability | High | Severe | High | IT Security Team | Implement multi-factor authentication; conduct regular audits | Pending Action | 2024-06-10
2024-04-15 | Regulatory changes in market entry | Medium | Moderate | Low | Legal & Compliance Team | Monitor regulatory updates; schedule compliance workshops | Planned | 2024-07-15