## Worksheet
Risk ID | Risk Description | Category | Impact Level | Likelihood | Risk Score (Impact x Likelihood) | Assigned Owner | Mitigation Strategy | Response Plan | Monitoring Frequency | Status | Last Reviewed Date
RISK-001 | Key vendor may fail to deliver critical components on time. | Supply Chain | High | Medium | 6 | Project Manager | Identify backup vendors and pre-qualify alternatives. | Escalate to procurement if delivery delay exceeds 10 days. | Monthly | Active | 2024-03-15
RISK-002 | Scope creep may lead to budget overruns. | Scope & Change | High | <>Medium | 6 | Change Control Board (CCB) | Implement formal change request process with cost-benefit analysis. | All changes require CCB approval and impact assessment. | Bi-weekly | Open | 2024-03-10
RISK-003 | Security breach due to outdated software in development environment. | Security | Critical | High | 12 | IT Security Lead | Patch all systems quarterly; conduct penetration testing. | Implement network segmentation and access controls. | Quarterly | High Priority | 2024-03-05
RISK-004 | Key team member may leave before project completion. | Human Resources | Medium | High | 6 | HR Manager | Recruit backup personnel and document knowledge transfer. | Develop onboarding plan for replacement staff. | Monthly | Active | 2024-03-12