## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact(th) | Current Status | Owner | Mitigation Strategy | Response Plan | Detection Method | Review Date
RISK-001 | Failure of key vendor to deliver required components on time | Supply Chain | Medium | High | Active | Jane Smith | Schedule alternative sourcing and dual supplier setup | Monitor vendor performance weekly; escalate if delays exceed 5 days | Performance metrics and SLA tracking | 2024-03-15
RISK-002 | Data breach due to unpatched system vulnerabilities | Security | High | Very High | Pending Assessment | Michael Chen | Implement patch management protocol and conduct penetration testing quarterly | Nightly security scans and incident response plan activation upon detection | Automated vulnerability scanning tools | 2024-04-01
RISK-003 | Scope creep during project execution | Project Management | Medium | Moderate | Monitoring | Sarah Lee | Define formal change control process with stakeholder approval required | Monthly scope reviews and documentation of all changes | Change request logs and stakeholder feedback surveys | 2024-03-20