## Worksheet
Risk Identification | Risk Description | Impact Level | Probability | Risk Rating (Impact x Probability) | Mitigation Strategy | Responsible Party | Monitoring Frequency | Status
1. Scope Creep | Uncontrolled changes to project scope leading to delays and cost overruns. | High | Medium | 6 | Implement formal change control process with approval matrix. | Project Manager | Bi-weekly | Active
2. Resource Shortage | Critical team members unavailable due to unforeseen obligations. | Medium | High | <6 | Maintain resource backup list and cross-train staff. | HR & Project Manager | Monthly | Monitoring
3. Budget Overrun | <Unplanned expenditures exceeding approved budget. | High | Medium | 6 | Conduct monthly financial reviews and variance analysis. | Finance Lead | Monthly | Active
4. Technology Failure | Key systems or tools fail during critical project phases. | High | Medium | 6 | Deploy redundant systems and conduct regular system audits. | IT Director | Bi-weekly | Active
5. Stakeholder Resistance | Key stakeholders oppose project decisions or deliverables. | Medium | High | 6 | Engage stakeholders early with clear communication plans and value propositions. | Stakeholder Manager | Monthly | Monitoring
Total Risks Identified: |  |  |  | 5 | Template Version: Annual ¦ Purpose: Risk Management ¦ Template Type: Project Plan