## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Risk Score | Owner | Mitigation Strategy | Monitoring Frequency | Status
RM-001 | Project timeline delay due to vendor delivery issues | Operational Risk | High | Medium | 7 | Jane Smith | Schedule buffer and alternate vendor identification | Monthly review | Active
RM-002 | Security breach due to outdated software | Security Risk | High | High | 10 | Michael Chen | Software patching and penetration testing | Bi-weekly | Pending Action
RM-003 | Resource overallocation during critical phase | Resource Risk | Moderate | High | 6 | Lisa Wang | Reallocate tasks and adjust staffing plan | Weekly review | Planned
RM-004 | Scope creep due to stakeholder requests | Scope Risk | Moderate | Medium | 5 | David Brown | Formal change request process and approval workflow | Bi-monthly | Monitored